## Slide 1
For Internal Circulation Only – Confidential & Sensitive Content
MIS to AEP
Migration Strategy

## Slide 2
Briefing Agenda
01
Executive Summary
02
03
What is Included In The Move
04
How We Will Know It Worked
05
Current OPEX /AMC Spend
06
Migration Risk & Dependencies
07
08
Driving Success through TEAMs (Transformation, Engagement & Efficiency, Agility, Modernization)
Deliver Trusted & Innovative Digital Services for Everyone.
Information Technology
09
Next Steps
Technical Migration Plan
Cost Benefits
Why We Are Moving from MIS

## Slide 3
Executive Summary
“Retiring MIS, consolidating into AEP, and laying the foundation for our data lakehouse.”
3
RETIRE
Decommission the outdated, unsupported MIS platform (Oracle 11g, end-of-life hardware).
1
CONSOLIDATE
Migrate its data & reporting into our existing AEP/BI system one source of truth.
2
BUILD
Lay the clean foundation for the upcoming Data Lakehouse program.
Bottom Line: This is the fastest, lowest-risk first step toward a single, modern data platform , cutting cost, risk, and duplicate data along the way.
Driving Success through TEAMs (Transformation, Engagement & Efficiency, Agility, Modernization)
Deliver Trusted & Innovative Digital Services for Everyone.
Information Technology

## Slide 4
MIS → AEP | PROJECT PURPOSE
Why we are moving MIS to AEP
Make AEP the central platform for reporting and analytics.
Driving Success through TEAMs (Transformation, Engagement & Efficiency, Agility, Modernization)
Deliver Trusted & Innovative Digital Services for Everyone.
Information Technology
Duplicate Data
Same source data managed in both MIS and AEP simultaneously
Platform Risk
Oracle 11g and ageing hardware have limited vendor support
Higher Cost
Separate licences, support, power and operations repeat every year
Slower Change
Two platforms require duplicate fixes and development effort

## Slide 5
MIS → AEP | SCOPE AND CONTROLS
What is included in the move
Review every MIS item and decide what happens next.
REVIEW THESE ITEMS
• Data feeds
• Materialized views & stored procedures
• ETL jobs and data transformations
• Dashboards and reports
• APIs
KEEP CONTROL DURING THE MOVE
• Move required historical data to AEP
• Keep audit and regulatory data safe
• Decide what to move, rebuild, combine, archive or retire
• Keep critical MIS processes running until AEP is ready
TEMPORARY EXCLUSIONS
If an item cannot move now, record the owner, reason, risk, target date and
retirement plan. Keep MIS running until checks, testing, user acceptance and
parallel operation are complete.
• Application integrations connected to MIS

## Slide 6
MIS → AEP | SUCCESS MEASURES
How we will know it worked
The migration will be considered successful when
AEP IS READY
• Approved MIS reports and workloads are available from AEP.
• Counts, totals and business rules match
• Refresh and response targets are met
• Duplicate data and processing are reduced
• Users and downstream applications are successfully redirected
to AEP
MIS CAN CLOSE
• History is moved or securely archived
• Expected infrastructure and license savings are confirmed
• Reports and services are working correctly in AEP
• Business and technical owners approve retirement
SHARED OWNERSHIP
AEP, MIS, business, infrastructure, security and source-system teams govern
the work together. The migration charter records the final scope and measures.

## Slide 7
Current OPEX / AMC Spend
Recurring annual cost of platforms and licenses currently in operation
RECURRING EVERY YEAR
$79,174
OPEX
Item
Qty
Each
Total
Oracle Golden-Gate
8
$998.40
$7987.20
Oracle Database Enterprise Edition
8
$1398.45
$11187.60
Subtotal (USD)
$79,174
Driving Success through TEAMs (Transformation, Engagement & Efficiency, Agility, Modernization)
Deliver Trusted & Innovative Digital Services for Everyone.
Information Technology
Item
Qty
Each
Total
Dorado Storage [one time]
30
$1650
$49500
Subtotal (USD)
$83,500.60
Other factors contributing to the cost
Energy & Power (data center)
Rack & Hardware Maintenance
Backup maintenance
Oracle Premier Support (hardware and OS)
Dedicated Headcount ,2 FTE (2 × $2,500/mo × 12)
2
$2500*12
$60000
ONE-TIME CAPEX (CAPITALISED)
SPARC T5 servers –book value is zero
2
$17000
$34000

## Slide 8
5-Year Net Savings
Annual run-rate savings, one-time transition cost, and net savings over a 5-year horizon
Annual Run-Rate Savings
$79,174 / yr
Resource savings (Managed Service 2 FTE ) = $60,000
Licence savings (Oracle GoldenGate + Database) = $19,174
One-Time Transition Cost
$64,800
Additional 2 developers for 6-month transition/handover
2 × $5400/mo (additional) × 6 months = $64,800
5-Year Total Cost of Ownership (Net Savings)
Year | Annual Savings | One-Time Cost | Net Savings | Cumulative Savings
Year 1 | $79,174 | ($64,800) | $14,574 | $14,574
Year 2 | $79,174 | – | $79,174 | $93,748
Year 3 | $79,174 | – | $79,174 | $172,922
Year 4 | $79,174 | – | $79,174 | $252,096
Year 5 | $79,174 | – | $79,174 | $331,270
$331,270
net savings over 5 years after absorbing the one-time $64,800 transition cost
Energy Savings
Lower power & cooling draw from consolidated infrastructure.
HW Maintenance
Reduced AMC spend on ageing, unsupported hardware.
Reduced ESB Load
Fewer integration hops lighten the ESB and improve throughput.
Architecture Consolidation
Fewer platforms to license, patch and operate.
Scalability & Maintenance
Elastic scaling cuts manual tuning and DBA overhead.
OTHER BENEFITS
Driving Success through TEAMs (Transformation, Engagement & Efficiency, Agility, Modernization)
Deliver Trusted & Innovative Digital Services for Everyone.
Information Technology

## Slide 9
Migration Risks & Dependencies
RISKS IDENTIFIED
3 High / 2 Medium
# | Risk Area | Description | Action Required | Impact
1 | Interface Dependency | CIM view is exposed from Legacy today. Post-migration, the AEP view must be exposed from THC instead. | Validate feasibility of exposing the required views from both Legacy and THC before cutover. | High
2 | AEP License Capacity | Existing AEP system is already running high on license usage, with no current headroom. | Clean up existing license allocation before onboarding additional data feeds. | Medium
3 | Delivery Resourcing | Migration development work requires dedicated, hands-on technical resourcing. | Onboard 2 developers on-site for the duration of the development phase. | Medium
4 | AEP DB Performance | AEP database may experience slowness once MIS workloads are migrated onto it. | Load-test AEP DB capacity and plan tuning/scaling ahead of migration. | High
5 | Reporting Continuity | GG based CAF reports currently depend on the existing MIS setup. | Define and validate the delivery mechanism for CAF reports post-migration. | High
Recommendation: Resolve the Legacy/THC interface dependency and validate AEP DB capacity before migration go-live
Driving Success through TEAMs (Transformation, Engagement & Efficiency, Agility, Modernization)
Deliver Trusted & Innovative Digital Services for Everyone.
Information Technology

## Slide 10
MIS currently acts as a central reporting repository. It receives data from multiple operational systems through file transfers, database links and Oracle Golden-Gate replication. MIS then processes this data and provides datasets to reports, dashboards, APIs and other downstream applications.
Current Data Integration Architecture
Integration type | Approximate volume | Current operation | Migration requirement | Complexity
File-based feeds | 15+ feeds | Source systems generate files and transfer them to MIS for scheduled loading. | Rebuild file ingestion in AEP, including file validation, scheduling, error handling and reconciliation. | Medium
Database links | To be confirmed | MIS directly reads data from selected Oracle databases through database links. | Identify every database link and replace it with an approved AEP ingestion method. | High
Oracle GoldenGate | 150 feeds | GoldenGate continuously or periodically replicates source-system data into MIS. | Map replicated tables to AEP, configure new replication routes and validate data consistency. | High
MIS processing | To be assessed | Procedures, ETL jobs and scheduled processes apply transformations and business rules. | Rebuild, optimize or retire the processing logic in AEP. | High
Reporting layer | To be assessed | Qlik QVFs, dashboards, reports, APIs and applications consume data from MIS. | Redirect consumers to AEP after data validation and business acceptance. | High
Historical data | To be assessed | MIS stores historical information required for reporting, audit and analysis. | Decide what history to migrate, archive or retain temporarily. | Medium to High
Driving Success through TEAMs (Transformation, Engagement & Efficiency, Agility, Modernization)
Deliver Trusted & Innovative Digital Services for Everyone.
Information Technology
Current MIS Architecture and Migration Complexity

## Slide 11
MIS to AEP Migration
High Level Technical Migration Plan - Oracle MIS → AEP | ~24 Weeks
1
Assessment &
Planning
~3 weeks
Assess data volume, growth, history & retention requirements
Assess data quality & known reconciliation issues
Define scope, RACI & success KPIs
Estimate AEP capacity, infrastructure & license requirements
2
Data Analysis &
Mapping
~5 weeks
Map Oracle tables and views to AEP Vertica entities
Identify table, job and report dependencies
Identify duplicate and obsolete data objects
3
Migration
~5 weeks
APIs, file interfaces
Database tables, materialized views & stored procedures
Migrate Historical data required for reporting, audit and regulatory purposes
4
Development
~6 weeks
Source-system data feeds and ingestion processes
ETL jobs, scheduled processes and data transformations
Application integrations connected to MIS
Tune AEP DB query & refresh performance
5
Testing &
Validation
~3 weeks
MIS vs AEP data reconciliation
SIT: ETL pipeline & integration tests
UAT: Data counts, and business rules are reconciled and signed off.
Performance & load testing on AEP DB
6
Deployment &
Go-Live
~2 weeks
Production cutover of GoldenGate/ETL pipelines
Deploy newly developed AEP reports/dashboards to production
Parallel run: legacy MIS + AEPside-by-side
Final cutover; decommission Oracle MIS
7
Post Go-Live
Support
Ongoing
Monitor pipeline jobs, AEP DB perf & SLAs
L1/L2 triage of residual Oracle 11g defects
User training
Continuous optimisation
Driving Success through TEAMs (Transformation, Engagement & Efficiency, Agility, Modernization)
Deliver Trusted & Innovative Digital Services for Everyone.
Information Technology
Map historical-data & retention requirements

## Slide 12
Next Steps | Immediate Action Required
1
Stakeholder Sign-Off
Secure executive approval from Finance, Technology & Operations. Agree governance model and data ownership.
2
Proof of Concept
Confirm AEP already holds the same MIS data, plus additional datasets, and validate reconciliation accuracy against existing reports.
3
Procurement & Licensing
Provision incremental AEP/Dorado storage for migrated workloads if required. Initiate licence exit and termination of Oracle 11g, Golden-Gate
4
Delivery Team
Assemble cross-functional delivery team , Data Engineer, Architect. Arrange travel & onsite presence for 2 developers during the build phase.
Driving Success through TEAMs (Transformation, Engagement & Efficiency, Agility, Modernization)
Deliver Trusted & Innovative Digital Services for Everyone.
Information Technology

## Slide 13
The Time to Act
Is Now